## Worksheet
Task ID | Task Name | Start Date | End Date | Status | Assigned To
T001 | Define Event Scope & Objectives | 2023-10-01 | 2023-10-05 | In Progress | Jane Smith
T002 | Secure Venue & Confirm Availability | 2023-10-06 | 2023-10-15 | Pending | Mark Johnson
T003 | Create Event Budget & Approval Process | 2023-10-16 | 2023-10-25 | Pending | Sarah Lee
T004 | Develop Marketing & Promotion Plan | 2023-10-18 | 2023-11-15 | Pending | Lisa Brown
T005 | Finalize Speaker & Guest List | 2023-11-01 | 2023-11-10 | Pending | David Wilson
T006 | Coordinate Catering & Logistics | 2023-11-16 | 2023-11-30 | Pending | Amy Garcia
T007 | Send Invitations & Track RSVPs | 2023-11-20 | 2023-12-15 | Pending | Jessica Taylor
T008 | Run Final Event Rehearsal | 2023-12-16 | 2023-12-17 | Pending | Ryan Clark
T009 | Execute Event Day Plan & Onsite Management | 2023-12-18 | 2023-12-18 | Pending | All Team Members
T010 | Post-Event Survey & Debrief Meeting | 2023-12-19 | 2023-12-25 | Pending | All Team Members