## Worksheet
Event Planning - Project Timeline (Detailed)
Phase | Task | Start Date | End Date | Status | Responsible Team/Person(Role)
Planning & Preparation Phase (All tasks must be completed before Event Execution)
Initial Planning | Define event objectives and scope | 2024-01-05 | 2024-01-15 | In Progress | Project Manager / Event Lead
Initial Planning | Create preliminary budget proposal | 2024-01-10 | 2024-01-20 | In Progress | Finance Team / Budget Coordinator
Venue & Logistics Phase
Venue Sourcing | Research and shortlist potential venues | 2024-01-18 | 2024-01-31 | Pending | Venue Coordinator / Logistics Manager
Venue Sourcing | Finalize venue contract and secure booking | 2024-02-01 | 2024-02-15 | Pending | Event Manager / Legal Advisor
Marketing & Communications Phase
Marketing Strategy | Develop marketing plan and messaging framework | 2024-01-25 | 2024-02-10 | In Progress | Marketing Director / Brand Manager
Communication Campaigns | Create promotional materials (digital and print) | 2024-02-16 | 2024-03-15 | Pending | Design Team / Copywriter
Participant & Speaker Coordination Phase
Registration System Setup | Configure online registration platform (e.g., Eventbrite, HubSpot) | 2024-03-18 | 2024-03-31 | Pending | IT Support / Admin Team
Speaker Engagement | Send invitations and confirm speaker commitments | 2024-03-15 | 2024-04-15 | Pending | Sponsorship & Outreach Manager / Program Coordinator
Event Execution Phase (Final 30 Days)
Final Preparations | Confirm all vendor contracts and deliverables | 2024-05-01 | 2024-05-15 | Pending | Operations Manager / Vendor Coordinator
On-Site Coordination | Conduct final walkthrough and site setup rehearsal | 2024-05-18 | 2024-05-24 | Pending | Floor Manager / Production Lead
Post-Event Phase (Immediate & Long-Term)
Post-Event Survey | Send feedback survey to attendees and stakeholders | 2024-05-25 | 2024-06-01 | Pending | CX Manager / Research Analyst
Performance Review & Reporting | Analyze event metrics and prepare final report for stakeholders | 2024-06-02 | 2024-06-15 | Pending | Project Manager / Data Analyst
Note:This timeline is a living document and subject to updates based on project progress. Status indicators reflect the current state as of the last review date.