## Event Planning Project Timeline
Event Planning Project Timeline
Task ID | Task Name | Start Date | End Date | Status | Responsible Person | Description th>
101 | Define Event Scope | 2025-04-01 | 2025-04-05 | Not StartedIn ProgressCompleted | John Doe | Outline goals, audience, and deliverables.
102 | Secure Venue | 2025-04-06 | 2025-04-15 | Not StartedIn ProgressCompleted | Jane Smith | Book and confirm location with contract.
103 | Develop Budget | 2025-04-16 | 2025-04-20 | Not StartedIn ProgressCompleted | Mike Johnson | Estimate costs and allocate funds.
104 | Invitations & RSVPs | 2025-04-21 | 2025-05-10 | Not StartedIn ProgressCompleted | Sarah Lee | Design, send, and track RSVPs.
105 | Hire Vendors | 2025-04-25 | 2025-05-15 | Not StartedIn ProgressCompleted | Alex Brown | Contract caterers, decorators, and performers.
106 | Finalize Program & Schedule | 2025-05-16 | 2025-05-23 | Not StartedIn ProgressCompleted | Linda White | Confirm speakers, timing, and flow.
107 | Event Execution & Onsite Management | 2025-05-24 | 2025-05-31 | Not StartedIn ProgressCompleted | Team Lead (All) | Oversee all on-site activities and logistics.
108 | Post-Event Review & Reporting | 2025-06-01 | 2025-06-10 | Not StartedIn ProgressCompleted | John Doe | Gather feedback and summarize results.