## Worksheet
Phase | Task | Start Date | End Date | Responsible Person | Status | Notes
Planning & Preparation | Define Event Objectives and Scope | 2023-10-01 | 2023-10-05 | Jane Doe | In Progress
Planning & Preparation | Set Budget and Allocate Funds | 2023-10-06 | 2023-10-10 | John Smith | Not Started | Budget approval pending from finance team.
Campaign & Promotion | Create Marketing Materials and Social Media Campaigns | 2023-10-11 | 2023-10-25 | Emily Johnson | In Progress | Flyers and digital banners in draft stage.
Campaign & Promotion | Launch Email Campaign to Target Audience | 2023-10-26 | 2023-11-05 | Lisa Brown | Not Started | Email list finalization scheduled for 10/24.
Venue & Logistics | Book Venue and Confirm Capacity | 2023-10-15 | 2023-10-20 | David Lee | In Progress | Venue options reviewed; contract to be signed by 10/18.
Venue & Logistics | Arrange Catering and On-Site Services | 2023-10-21 | 2023-10-31 | Rachel Green | Not Started | Catering vendors to be selected by 10/25.
Event Execution | Finalize Event Schedule and Speaker Confirmations | 2023-11-06 | 2023-11-15 | Jane Doe | Not Started | Schedule template shared; speaker confirmations in process.
Event Execution | Conduct Full Event Rehearsal and Technical Check | 2023-11-16 | 2023-11-17 | Mike Taylor | Not Started | Tech team meeting scheduled for 11/08.
Closing & Review | Post-Event Survey Distribution and Data Collection | 2023-11-20 | 2023-11-25 | Lisa Brown | Not Started | Survey template ready; distribution begins post-event.
Closing & Review | Conduct Post-Event Debrief Meeting and Report Finalization | 2023-11-26 | 2023-11-30 | Jane Doe | Not Started | Mandatory team meeting to review KPIs and feedback.