## Worksheet
Event Planning - Project Timeline (Financial View)
Task | Timeline |  |  | Budget Allocation |  | Status
| Start Date | End Date | Dur. (Days) | Estimated Cost ($) | Actual Cost ($)
Define Event Objectives | 2024-01-05 | 2024-01-10 | 6 | $5,000 | $4,850 | Completed
Secure Venue & Permits | 2024-01-11 | 2024-01-31 | 21 | $35,000 | $36,575 | Completed
Finalize Vendor Contracts | 2024-01-15 | 2024-02-15 | 31 | $75,000 | $73,899 | Completed
Marketing & Promotions | 2024-01-20 | 2024-03-31 | 71 | $65,000 | $68,955 | Upcoming
Attendee Registration & Management | 2024-02-01 | 2024-04-30 | 99 | $35,000 | $37,685 | Upcoming
On-Site Logistics & Setup | 2024-04-15 | 2024-05-31 | 47 | $85,000 | $83,996 | Upcoming
Event Execution & Management | 2024-05-01 | 2024-05-31 | 31 | $98,500 | $96,743 | Upcoming
Post-Event Reporting & Evaluation | 2024-06-01 | 2024-06-15 | 15 | $8,500 | $8,397 | Upcoming
Total Budget Overview: | $400,000 |  |  |  | $413,298
Budget Variance: |  |  |  |  | +$13,298
Note:All dates are in YYYY-MM-DD format. Budget variance is calculated as Actual Cost minus Estimated Cost.