## Worksheet
Event Planning - Project Timeline (Freelancer Style)
Task | Start Date | End Date | Status | Responsible Party
Initial Planning & Concept Development | 2024-01-05 | 2024-01-15 | In Progress | Alice Johnson (Project Lead)
Vendor Selection & Contracts | 2024-01-16 | 2024-01-31 | Pending | Michael Reed (Logistics)
Event Venue Booking & Confirmation | 2024-01-25 | 2024-01-31 | In Progress | Sarah Kim (Operations)
Catering & Menu Finalization | 2024-02-01 | 2024-02-15 | Pending | Carlos Mendez (Cuisine)
Invitation Design & Distribution | 2024-02-10 | 2024-03-15 | In Progress | Laura Chen (Marketing)
Schedule & Program Finalization | 2024-03-16 | 2024-03-31 | In Progress | Alice Johnson (Project Lead)
On-Site Setup & Rehearsal | 2024-04-15 | 2024-04-17 | In Progress | Michael Reed (Logistics)
Event Day Coordination & Execution | 2024-04-18 | 2024-04-18 | Pending | All Team Members
Post-Event Review & Reporting | 2024-04-19 | 2024-04-30 | Pending | Alice Johnson (Project Lead)
This timeline is designed for freelancers managing event planning projects with clear phases, responsibilities, and deadlines.