## Worksheet
Event Planning - Project Timeline (Home Use)
Phase | Task | Start Date | End Date | Status | Responsible Person
Planning & Research | Determine event type and theme | 2024-04-01 | 2024-04-05 | Pending | John Doe
Planning & Research | Set budget and allocate funds | 2024-04-06 | 2024-04-10 | In Progress | Jane Smith
Vendor Coordination | Select and book caterer | 2024-04-11 | 2024-04-15 | Pending | John Doe
Vendor Coordination | Book venue and confirm availability | 2024-04-12 | 2024-04-18 | In Progress | Jane Smith
Marketing & Communication | Create event invitations and digital ads | 2024-04-19 | 2024-04-25 | Pending | Alice Johnson
Marketing & Communication | Distribute invitations and promote event | 2024-04-26 | 2024-05-03 | Pending | Alice Johnson
Logistics & Setup | Arrange transportation and parking details | 2024-05-04 | 2024-05-10 | Pending | Robert Brown
Logistics & Setup | Prepare event signage and decor layout | 2024-05-11 | 2024-05-15 | Pending | Mary Davis
Event Day Execution | Final walkthrough and site inspection | 2024-05-16 | 2024-05-17 | Pending | All Team Members
Event Day Execution | Host the event and manage on-site activities | 2024-05-18 | 2024-05-18 | Pending | All Team Members
Post-Event Follow-Up | Gather feedback from attendees and vendors | 2024-05-19 | 2024-05-23 | Pending | Jane Smith
Post-Event Follow-Up | Submit final report and thank-you notes | 2024-05-24 | 2024-05-31 | Pending | John Doe