## Worksheet
Event Planning Project Timeline
Phase | Task | Start Date | End Date | Status | Responsible Team/Person
Planning & Setup | Define Event Objectives & Scope | 2023-10-01 | 2023-10-05 | In Progress | Project Manager (Sarah)
Venue & Logistics | Book Venue & Confirm Availability | 2023-10-06 | 2023-10-15 | Pending | Venue Coordinator (James)
| Arrange Catering & Transportation | 2023-10-16 | 2023-10-25 | Pending | Catering Team (Lisa)
Marketing & Promotion | Design Marketing Materials | 2023-10-18 | 2023-10-28 | In Progress | Marketing Team (Mike)
| Create Social Media Campaign | 2023-10-29 | 2023-11-15 | Pending | Social Media Manager (Anna)
| Send Invitations & Confirm RSVPs | 2023-11-01 | 2023-11-25 | Pending | Event Coordinator (David)
On-Site Execution | Finalize Setup & Stage Design | 2023-11-26 | 2023-11-30 | Pending | Production Manager (Tom)
| Run Dry Rehearsal & Tech Check | 2023-12-01 | 2023-12-05 | Pending | Tech Lead (Rachel)
Event Day & Wrap-Up | Host Event (Main Day) | 2023-12-06 | 2023-12-06 | Pending | All Teams (Joint Effort)
Post-Event | Collect Feedback & Survey Participants | 2023-12-07 | 2023-12-15 | Pending | Data Analyst (Chris)
| Final Report & Budget Review | 2023-12-16 | 2023-12-31 | Pending | Finance Manager (Elena)
Timeline Status Update as of October 1, 2023 – Project Overall Progress: 35%