## Worksheet
Event Planning - Project Timeline - Manager View
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | % Complete
T001 | Define Event Scope & Objectives | Project Manager | 2024-04-05 | 2024-04-15 | Confirmed | 100%
T002 | Finalize Budget Approval | Finance Lead | 2024-04-16 | 2024-04-30 | Pending | 35%
T003 | Select Venue & Book Date | Logistics Coordinator | 2024-04-18 | 2024-05-15 | Pending | 65%
T004 | Finalize Vendor Contracts | Venue Manager | 2024-05-16 | 2024-06-15 | Pending | 10%
T005 | Develop Marketing Campaign | Marketing Director | 2024-06-18 | 2024-07-15 | Pending | 5%
T006 | Send Invitations & Confirm RSVPs | Event Coordinator | 2024-07-16 | 2024-08-15 | Pending | 0%
T007 | Event Day Setup & Final Checks | Safety Officer | 2024-08-16 | 2024-08-17 | Pending | 0%
T008 | Post-Event Review & Reporting | Project Manager | 2024-08-18 | 2024-09-15 | Pending | 0%
Event Planning Timeline - Manager View ¦ Last Updated: April 5, 2024 ¦ Project ID: EP-2024-01