## Worksheet
Task ID | Task Description | Start Date | End Date | Assignee | Status
Phase 1: Event Planning & Strategy (Weeks 1-4)
TP-001 | Define event objectives and target audience | 2023-10-02 | 2023-10-06 | Alice Johnson | In Progress
TP-002 | Select event theme and venue (finalized) | 2023-10-09 | 2023-10-13 | Mike Chen | Completed
Phase 2: Logistics & Vendor Coordination (Weeks 5-8)
TP-003 | Book catering and audiovisual services | 2023-10-16 | 2023-10-27 | Sarah Williams | In Progress
M-01 | Vendor contracts signed (Deadline) | 2023-10-27 | 2023-10-27 | All Leads | On Track
Phase 3: Marketing & Promotion (Weeks 9-12)
TP-004 | Design digital and print promotional materials | 2023-10-30 | 2023-11-17 | Daniel Reed | Not Started
M-02 | Launch marketing campaign (Online & Email) | 2023-11-18 | 2023-11-18 | Daniel Reed | Pending
Phase 4: Final Preparation & Event Execution (Weeks 13-16)
TP-005 | Conduct on-site walkthrough and tech rehearsal | 2023-12-04 | 2023-12-15 | Alice Johnson, Mike Chen | Pending
M-03 | Final event setup and team briefing (Day before) | 2023-12-19 | 2023-12-19 | All Team Members | Pending
Event Day & Post-Event (Week 17)
M-04 | Host the main event | 2023-12-21 | 2023-12-21 | All Staff | Pending
M-05 | Post-event feedback collection and wrap-up report | 2023-12-25 | 2023-12-30 | Alice Johnson | Pending
Total Duration: |  |  |  | 17 Weeks (Oct 2 - Dec 30, 2023)