## Event Planning Project Timeline
Event Planning Project Timeline
Task | Start Date | End Date | Status | Responsible Party
Project Kickoff & Planning | 2023-10-01 | 2023-10-05 | In Progress | Project Manager
Define Event Objectives & Scope | 2023-10-06 | 2023-10-10 | In Progress | Event Coordinator
Select Venue & Book Reservation | 2023-10-11 | 2023-10-18 | To Do | Venue Manager
Finalize Budget & Approvals | 2023-10-19 | 2023-10-25 | To Do | Finance Team
Develop Marketing & Promotion Plan | 2023-10-26 | 2023-11-05 | To Do | Marketing Specialist
Confirm Speakers & Guest List | 2023-11-06 | 2023-11-15 | To Do | Event Coordinator
Create Event Schedule & Agenda | 2023-11-16 | 2023-11-25 | To Do | Program Manager
Distribute Event Materials & Invitations | 2023-11-26 | 2023-12-05 | To Do | Administrative Staff
Finalize Logistics & Vendor Contracts | 2023-12-06 | 2023-12-15 | To Do | Logistics Coordinator
Event Setup & Rehearsal Day | 2023-12-16 | 2023-12-17 | To Do | Setup Team, Event Coordinator
Event Day: Execution & Management | 2023-12-18 | 2023-12-18 | To Do | All Team Members
Post-Event Review & Reporting | 2023-12-19 | 2023-12-25 | To Do | Project Manager, Finance Team
Legend:
•Milestone Tasks: Key deliverables with significant impact
• Status: To Do / In Progress / Completed