## Worksheet
Event Planning - Project Timeline
Task | Description | Responsible Person | Start Date | End Date | Status
Define Event Scope & Objectives | Establish event goals, target audience, and expected outcomes. | Project Manager | 2024-04-05 | 2024-04-10 | Pending
Select Venue & Confirm Booking | Research and secure an appropriate venue based on capacity and budget. | Logistics Coordinator | 2024-04-11 | 2024-04-18 | In Progress
Develop Event Theme & Branding | Create visual identity including colors, logo, and design elements. | Marketing Designer | 2024-04-15 | 2024-04-25 | In Progress
Invite Guests & Manage RSVPs | Send out invitations and track attendee responses. | Event Coordinator | 2024-04-20 | 2024-05-15 | Pending
Arrange Catering & Logistics | Finalize food, beverages, and on-site setup. | Catering Manager | 2024-04-22 | 2024-05-10 | In Progress
Plan Program & Schedule Activities | Develop the detailed event agenda and speaker lineup. | Schedule Lead | 2024-04-28 | 2024-05-18 | Pending
Coordinate Technology & AV Setup | Arrange for sound, lighting, presentation systems, and streaming. | AV Technician | 2024-05-01 | 2024-05-23 | Pending
Conduct Final Review & Dry Run | Perform a full rehearsal and verify all components. | Project Manager | 2024-05-24 | 2024-05-26 | Pending
Host Event Day Activities | Execute event according to schedule with real-time management. | All Team Members | 2024-05-27 | 2024-05-27 | Pending
Post-Event Evaluation & Reporting | Gather feedback and compile performance report. | Project Manager | 2024-05-28 | 2024-06-03 | Pending
Personal Use Template – Event Planning Project Timeline