## Worksheet
Task | Start Date | End Date | Assigned To | Status | Progress (%)
Define Event Goals | 2023-10-01 | 2023-10-05 | Project Manager | Completed | 100%
Choose Venue | 2023-10-06 | 2023-10-15 | Venue Coordinator | In Progress | 65%
Finalize Budget | 2023-10-08 | 2023-10-18 | Finance Lead | Pending | 0%
Book Vendors | 2023-10-16 | 2023-11-05 | Venue Coordinator | Not Started | 0%
Create Marketing Plan | 2023-10-20 | 2023-11-10 | Marketing Team | Not Started | 0%
Send Invitations | 2023-11-06 | 2023-11-20 | Event Coordinator | Not Started | 0%
Conduct Final Review | 2023-11-25 | 2023-11-30 | Project Manager | Not Started | 0%
Execute Event Day | 2023-12-01 | 2023-12-01 | Event Team | Not Started | 0%