## Event Planning Project Timeline
Event Planning Project Timeline
Phase | Task Description | Start Date | End Date | Status
Planning & Research | Define event objectives and target audience | 2023-10-01 | 2023-10-07 | In Progress
| Set budget and allocate resources | 2023-10-08 | 2023-10-14 | In Progress
| Research venues and select preferred option | 2023-10-15 | 2023-10-21 | Pending
| Confirm availability with selected venue | 2023-10-22 | 2023-10-28 | Pending
Logistics & Coordination | Book vendors (catering, decorations, audiovisual) | 2023-10-29 | 2023-11-05 | Pending
| Coordinate with speakers and performers | 2023-11-06 | 2023-11-13 | Pending
| Create event schedule and timeline draft | 2023-11-14 | 2023-11-20 | Pending
| Finalize logistics checklist and assign responsibilities | 2023-11-21 | 2023-11-27 | Pending
Promotion & Registration | Design promotional materials (flyers, digital banners) | 2023-11-28 | 2023-12-05 | Pending
| Launch registration portal and set up payment processing | 2023-12-06 | 2023-12-13 | Pending
| Begin marketing campaign (email, social media) | 2023-12-14 | 2023-12-28 | Pending
| Monitor registration numbers and adjust outreach as needed | 2023-12-29 | 2024-01-05 | Pending
Final Preparation | Conduct full venue walkthrough and setup mock-up | 2024-01-06 | 2024-01-12 | Pending
| Finalize speaker and staff briefings | 2024-01-13 | 2024-01-19 | Pending
| Confirm all materials and equipment delivery schedule | 2024-01-20 | 2024-01-26 | Pending
Event Execution & Wrap-Up | Day-of event: Setup and staff coordination | 2024-01-27 | 2024-01-27 | Pending
| Host the event and manage real-time operations | 2024-01-28 | 2024-01-28 | Pending
| Post-event: Gather feedback, close vendor contracts, and submit report | 2024-01-29 | 2024-02-05 | Pending
Total Duration: October 1, 2023 – February 5, 2024