## Event Planning Project Timeline
Event Planning Project Timeline
Task | Start Date | End Date | Assigned To | Status
Define Event Objectives & Scope | 2024-01-05 | 2024-01-10 | Jane Smith | Completed
Secure Venue & Confirm Booking | 2024-01-11 | 2024-01-25 | Mark Johnson | Pending
Finalize Event Program & Schedule | 2024-01-18 | 2024-01-31 | Sarah Lee | Pending
Coordinate Catering & Menu Approval | 2024-01-20 | 2024-02-15 | Lisa Wong | Pending
Arrange Audiovisual & Technical Setup | 2024-01-25 | 2024-02-10 | Tom Brown | Pending
Send Invitations & Manage RSVPs | 2024-02-01 | 2024-03-15 | Jane Smith | Pending
Finalize Vendor Contracts & Payments | 2024-02-10 | 2024-03-15 | Mark Johnson | Pending
Conduct Full Event Rehearsal | 2024-03-18 | 2024-03-19 | Sarah Lee | Pending
Execute Event Day Operations | 2024-03-25 | 2024-03-25 | All Team Members | Pending
Post-Event Evaluation & Reporting | 2024-03-26 | 2024-04-15 | Jane Smith | Pending