## Worksheet
Event Planning - Project Timeline Report
Task ID | Task Description | Responsible Team | Start Date | End Date | Status | % Complete
EVT-001 | Define Event Objectives and Scope | Planning Committee | 2023-10-01 | 2023-10-05 | In Progress | 75%
EVT-002 | Select Event Venue and Confirm Booking | Logistics Team | 2023-10-03 | 2023-10-15 | Completed | 100%
EVT-003 | Develop Marketing and Promotion Strategy | Marketing Team | 2023-10-16 | 2023-11-05 | In Progress | 45%
EVT-004 | Finalize Speaker and Panelist Invitations | Events Coordinator | 2023-10-18 | 2023-11-15 | Delayed | 60%
EVT-005 | Design and Print Event Materials (Invitations, Programs) | Design Team | 2023-11-01 | 2023-11-25 | In Progress | 35%
EVT-006 | Set Up Registration Portal and Launch Campaign | IT & Marketing | 2023-11-10 | 2023-11-30 | Completed | 100%
EVT-007 | Coordinate Catering and On-Site Logistics | Catering Manager | 2023-11-20 | 2023-12-15 | In Progress | 50%
EVT-008 | Conduct Full Rehearsal and Dry Run | Event Team Lead | 2023-12-16 | 2023-12-17 | In Progress | 85%
EVT-009 | Finalize Budget and Obtain Approvals | Finance Department | 2023-12-01 | 2023-12-18 | In Progress | 70%
EVT-010 | Post-Event Survey Distribution and Analysis | Research Team | 2023-12-19 | 2023-12-31 | Delayed (Pending Final Event Date) | 5%
Report Generated on: