## Event Planning Project Timeline
Event Planning Project Timeline
Task | Start Date | End Date | Status | Responsible Person
Define Event Goals and Objectives | 2023-10-01 | 2023-10-05 | Completed | Jane Doe
Select Event Date and Venue | 2023-10-06 | 2023-10-15 | In Progress | John Smith
Create Guest List and Send Invitations | 2023-10-16 | 2023-10-30 | Not Started | Sarah Lee
Plan Event Agenda and Schedule | 2023-10-18 | 2023-10-25 | Not Started | Lisa Wang
Coordinate Catering and Food Services | 2023-10-20 | 2023-11-05 | Not Started | Marcus Brown
Hire and Schedule Entertainment/Vendors | 2023-10-25 | 2023-11-10 | Not Started | Amanda Clark
Develop Marketing and Promotion Plan | 2023-10-30 | 2023-11-20 | Not Started | Daniel Young
Finalize Budget and Secure Funding | 2023-11-05 | 2023-11-15 | Not Started | Jessica Miller
Cleanup and Event Setup (Day Before) | 2023-11-24 | 2023-11-24 | Not Started | All Team Members
Event Day Execution and Management | 2023-11-25 | 2023-11-25 | In Progress | All Team Members
Post-Event Evaluation and Reporting | 2023-11-26 | 2023-11-30 | Not Started | Jane Doe