## Worksheet
Event Planning Project Timeline - Small Business
Task ID | Task Description | Responsible Party | Start Date | End Date | Status
101 | Define Event Objectives & Goals | Project Manager | 2025-04-01 | 2025-04-05 | In Progress
102 | Select Event Date & Venue | Event Coordinator | 2025-04-06 | 2025-04-15 | To Do
103 | Create Guest List & Invitations | Marketing Team | 2025-04-16 | 2025-04-25 | To Do
104 | Develop Event Budget & Approvals | Finance Manager | 2025-04-16 | 2025-04-30 | To Do
105 | Schedule Vendor Contracts (Catering, Decor) | Logistics Team | 2025-04-18 | 2025-05-10 | To Do
106 | Create Event Agenda & Program Flow | Event Coordinator | 2025-04-28 | 2025-05-15 | To Do
107 | Launch Marketing Campaign (Social Media, Email) | Marketing Team | 2025-05-01 | 2025-06-30 | To Do
108 | Finalize Guest RSVPs & Headcount | Event Coordinator | 2025-06-15 | 2025-07-14 | To Do
109 | Conduct Event Rehearsal & Setup Test | Logistics Team | 2025-07-15 | 2025-07-18 | To Do
110 | Event Day Execution & On-site Management | All Teams | 2025-07-20 | 2025-07-20 | To Do
111 | Post-event Survey & Feedback Collection | Project Manager | 2025-07-21 | 2025-07-30 | To Do
Total Duration: |  |  |  |  | 18 days (from 2025-04-01 to 2025-07-31)