## Worksheet
Event Planning Project Timeline - Startup Style
Phase | Task | Start Date | End Date | Status | Owner
Planning & Preparation
Phase 1 | Define Event Goals & Theme | 2023-10-05 | 2023-10-10 | Pending | Jane Doe
Phase 1 | Set Budget & Funding Sources | 2023-10-07 | 2023-10-15 | In Progress | Mike Smith
Marketing & Outreach
Phase 2 | Create Event Website & Landing Page | 2023-10-15 | 2023-10-25 | Pending | Lisa Chen
Phase 2 | Launch Social Media Campaigns | 2023-10-18 | 2023-11-05 | Pending | Alex Turner
Logistics & Operations
Phase 3 | Secure Venue & Permits | 2023-10-20 | 2023-11-10 | Pending | Sarah Johnson
Phase 3 | Arrange Catering & Equipment | 2023-11-01 | 2023-11-20 | Pending | Daniel Kim
Execution & Wrap-Up
Phase 4 | Finalize Speaker Confirmations | 2023-11-15 | 2023-11-25 | Pending | Jane Doe
Phase 4 | Conduct Event Dry Run & Tech Check | 2023-11-26 | 2023-11-30 | Pending | Mike Smith
Post-Event Activities
Phase 5 | Host the Event (Final Day) | 2023-12-01 | 2023-12-01 | Pending | All Team Members
Phase 5 | Send Follow-Up Surveys & Thank Yous | 2023-12-03 | 2023-12-10 | Pending | Lisa Chen