## Worksheet
Task | Start Date | End Date | Status | Responsible Party
Planning Phase (Jan 1 - Jan 15)
Define event objectives and scope | Jan 01, 2024 | Jan 03, 2024 | In Progress | Project Manager
Create initial budget proposal | Jan 04, 2024 | Jan 06, 2024 | Not Started | Finance Lead
Milestone: Finalize event concept and approval | Jan 15, 2024 | Jan 15, 2024 | Not Started | Project Manager
Logistics & Coordination (Jan 16 - Feb 10)
Secure venue and sign contract | Jan 16, 2024 | Jan 25, 2024 | In Progress | Logistics Coordinator
Book vendors (catering, AV, décor) | Jan 26, 2024 | Feb 05, 2024 | Not Started | Venue Manager
Milestone: Confirm all vendor contracts signed | Feb 10, 2024 | Feb 10, 2024 | Not Started | Venue Manager
Marketing & Communication (Jan 16 - Mar 1)
Develop event branding and promotional materials | Jan 20, 2024 | Feb 03, 2024 | In Progress | Marketing Team
Launch registration portal and email campaign | Feb 05, 2024 | Feb 15, 2024 | Not Started | Email Coordinator
Milestone: Achieve target registration count (500) | Mar 01, 2024 | Mar 01, 2024 | Not Started | Marketing Team
Final Preparations (Mar 2 - Mar 31)
Finalize event schedule and speaker confirmations | Mar 02, 2024 | Mar 10, 2024 | In Progress | Schedule Lead
Conduct venue walkthrough and tech rehearsal | Mar 15, 2024 | Mar 20, 2024 | Not Started | Tech Coordinator
Milestone: Final event readiness check complete | Mar 31, 2024 | Mar 31, 2024 | Not Started | All Teams
Event Day (Apr 5)
Milestone: Successful execution of event | Apr 05, 2024 | Apr 05, 2024 | Not Started | All Teams
Post-Event (Apr 6 - Apr 30)
Conduct post-event survey and feedback collection | Apr 06, 2024 | Apr 15, 2024 | Not Started | Satisfaction Team
Milestone: Submit final event report and financial summary | Apr 30, 2024 | Apr 30, 2024 | Not Started | Project Manager