## Worksheet
Event Planning Project Timeline - Team Use
Task ID | Task Name | Assigned To | Start Date | End Date | Status
T001 | Define Event Objectives | Team Lead - Alex Johnson | 2024-05-15 | 2024-05-17 | Completed
T002 | Secure Venue & Book Date | Logistics Team - Maria Lopez | 2024-05-18 | 2024-05-31 | In Progress
T003 | Develop Marketing Strategy | Marketing Team - James Wilson | 2024-05-18 | 2024-06-15 | In Progress
T004 | Finalize Guest List & Invitations | Events Coordinator - Sarah Chen | 2024-06-16 | 2024-07-15 | Pending
T005 | Coordinate Catering & Menu Approval | Catering Team - David Kim | 2024-06-18 | 2024-07-15 | Pending
T006 | Set Up Event Schedule & Timeline | Project Manager - Emily Rodriguez | 2024-07-16 | 2024-07-31 | Pending
T007 | Conduct Final Event Walkthrough | Team Lead - Alex Johnson | 2024-08-15 | 2024-08-16 | Pending
T008 | Event Execution & On-Site Management | Full Team - All Departments | 2024-08-17 | 2024-08-17 | Pending
T009 | Post-Event Feedback Collection & Report | Analysis Team - Olivia Brown | 2024-08-18 | 2024-08-31 | Pending