## Worksheet
Event Planning Project Timeline
Task ID | Task Description | Start Date | End Date | Status | Responsible Person
001 | Define Event Objectives | 2023-10-01 | 2023-10-05 | Completed | Jane Doe
002 | Select Event Date and Venue | 2023-10-06 | 2023-10-15 | In Progress | John Smith
003 | Create Event Budget Plan | 2023-10-16 | 2023-10-25 | Not Started | Alice Johnson
004 | Develop Marketing and Promotion Strategy | 2023-10-26 | 2023-11-15 | Not Started | Mike Brown
005 | Finalize Guest List and Send Invitations | 2023-11-16 | 2023-11-30 | Not Started | Sarah Wilson
006 | Coordinate Catering and Logistics | 2023-12-01 | 2023-12-15 | Not Started | Robert Taylor
007 | Event Day Setup and Staff Briefing | 2023-12-16 | 2023-12-16 | Not Started | Jane Doe
008 | Conduct Event and Manage On-Site Operations | 2023-12-17 | 2023-12-17 | Not Started | All Team Members
009 | Post-Event Review and Feedback Collection | 2023-12-18 | 2023-12-25 | Not Started | Alice Johnson
Template Version: 1.0 ¦ Purpose: Event Planning ¦ Project Timeline