## Worksheet
Event Planning - Project Timeline (Tracking View)
Task | Responsible | Start Date | End Date | Status | % Complete
Define Event Objectives & Scope | Jane Smith | 2024-01-05 | 2024-01-10 | In Progress | 75%
Secure Venue & Permits | Mark Johnson | 2024-01-11 | 2024-01-25 | Pending | 0%
Develop Event Theme & Branding | Lisa Chen | 2024-01-15 | 2024-01-30 | In Progress | 65%
Create Marketing & Promotion Plan | Derek Brown | 2024-01-20 | 2024-02-15 | Pending | 5%
Finalize Budget & Sponsorships | Sarah Lee | 2024-01-28 | 2024-02-10 | Pending | 15%
Recruit & Schedule Staff/Volunteers | Tom Wilson | 2024-02-01 | 2024-02-18 | Pending | 10%
Confirm Speakers & Performers | Karen Davis | 2024-02-05 | 2024-03-15 | Pending | 8%
Organize Event Logistics (AV, Setup) | Mike Roberts | 2024-02-15 | 2024-03-31 | Pending | 18%
Conduct Final Event Walkthrough | Jane Smith | 2024-03-30 | 2024-04-15 | Pending | 5%
Execute & Monitor Event Day Operations | All Team Members | 2024-04-16 | 2024-04-16 | Pending | 0%
Post-Event Evaluation & Reporting | Sarah Lee | 2024-04-17 | 2024-04-30 | Pending | 3%