## Worksheet
Event Planning - Project Tracker (Advanced)
Task ID | Task Description | Assigned To | Due Date | Status | Prioritization | Budget Allocated ($)
EVT-001 | Finalize event theme and concept | Jane Smith | 2023-10-15 | Pending | High | 1,500
EVT-002 | Book venue and confirm capacity | Mike Johnson | 2023-10-18 | In Progress | High | 8,500
EVT-003 | Send invitations to stakeholders | Sarah Williams | 2023-11-01 | In Progress | Medium | 450
EVT-004 | Arrange catering and dietary options | David Brown | 2023-11-10 | Pending | High | 6,200
EVT-005 | Coordinate speaker schedules and confirmations | Lisa Garcia | 2023-11-15 | In Progress | Medium | 3,000
EVT-006 | Design and print event materials (banners, signage) | Chris Lee | 2023-11-25 | Pending | Low | 900
EVT-007 | Set up event registration portal | Tina Patel | 2023-11-30 | Completed | Medium | 2,800
EVT-008 | Conduct final walkthrough and logistics check | Jane Smith | 2023-12-05 | Pending | High | 1,800
Total Budget Allocated:$25,150
Tasks Completed:1 / 8
Status Overview:1 Completed, 3 In Progress, 4 Pending