## Worksheet
Event Planning - Project Tracker (Analysis View)
Task ID | Task Name | Owner | Due Date | Status | Priority | Budget Allocation ($)
#EV001 | Finalize Event Concept & Theme | Sarah Johnson | 2023-10-15 | In Progress | High | 1,500
#EV002 | Book Venue & Confirm Availability | Michael Chen | 2023-10-18 | Pending | High | 5,000
#EV003 | Develop Marketing & Promotion Plan | Lisa Park | 2023-11-01 | In Progress | Medium | 3,200
#EV004 | Finalize Vendor Contracts (Catering, AV) | James Wilson | 2023-11-05 | Pending | High | 8,500
#EV005 | Send Invitations & Track RSVPs | Emily Davis | 2023-11-15 | Pending | Medium | 1,800
#EV006 | Coordinate Event Day Logistics | Taylor Brown | 2023-11-25 | Pending | High | 4,000
#EV007 | Post-Event Feedback Collection | Ryan Moore | 2023-12-15 | Pending | Low | 600
Total Budget Allocated: | [5 empty] | $24,600