## Worksheet
Event Planning - Project Tracker
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Priority
T001 | Select Venue | Jane Smith | 2023-10-05 | 2023-10-15 | In Progress | High
T002 | Send Invitations | John Doe | 2023-10-16 | 2023-10-30 | Not Started | Medium
T003 | Hire Catering Service | Sarah Lee | 2023-10-18 | 2023-11-05 | In Progress | High
T004 | Arrange Entertainment | Mike Brown | 2023-10-20 | 2023-11-10 | Not Started | Medium
T005 | Create Event Schedule | Lisa Wong | 2023-11-01 | 2023-11-15 | In Progress | High
T006 | Finalize Budget Approval | David Kim | 2023-11-05 | 2023-11-20 | In Progress | High
T007 | Confirm Attendees RSVPs | Jane Smith | 2023-11-15 | 2023-11-30 | Not Started | Medium
Notes:This is a sample project tracker for event planning. Update statuses as tasks progress.