## Worksheet
Event Planning - Project Tracker
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Budget (USD)
T001 | Finalize Event Concept | Jane Smith | 2024-05-15 | 2024-05-20 | Completed | $1,500.00
T002 | Select Venue & Confirm Booking | Michael Brown | 2024-05-18 | 2024-05-31 | Pending | $7,500.00
T003 | Design Invitations & Marketing Materials | Sarah Johnson | 2024-05-21 | 2024-06-15 | Pending | $3,800.00
T004 | Secure Catering & Menu Approval | David Lee | 2024-05-25 | 2024-06-10 | Pending | $6,900.00
T005 | Arrange Audio/Visual Equipment & Tech Support | Emily Chen | 2024-06-01 | 2024-06-18 | Pending | $3,500.00
T006 | Confirm Speaker & Guest Lineup | Alex Turner | 2024-06-15 | 2024-06-30 | Pending | $5,200.00
T007 | Finalize Event Schedule & Run-Through | Jane Smith | 2024-06-18 | 2024-06-30 | Pending | $1,800.00
T008 | Event Day Coordination & On-Site Management | Michael Brown | 2024-07-15 | 2024-07-15 | Delayed | $8,600.00
Generated on¦ Total Project Budget: $45,500.00