## Worksheet
Event Planning - Daily Project Tracker
Date | Event Name | Task Description | Status | Assigned To | Deadline | Progress (%)
2024-04-05 | Annual Tech Conference 2024 | Finalize venue contract and payment | Pending | Sarah Johnson | 2024-04-10 | 35%
2024-04-05 | Annual Tech Conference 2024 | Create event agenda and schedule | In Progress | Mike Chen | 2024-04-15 | 60%
2024-04-06 | Spring Networking Mixer | Send invitations to 150+ guests | Pending | Lisa Rodriguez | 2024-04-12 | 15%
2024-04-06 | Spring Networking Mixer | Secure catering and beverage options | In Progress | James Wilson | 2024-04-18 | 50%
2024-04-07 | Product Launch Event | Develop presentation and demo scripts | In Progress | Amy Thompson | 2024-04-17 | 80%
2024-04-07 | Product Launch Event | Confirm speaker lineup and travel arrangements | Pending | David Lee | 2024-04-19 | 10%
2024-04-08 | Celebration Gala Night | Book entertainment and performers | Pending | Olivia Martinez | 2024-04-16 | 5%
2024-04-08 | Celebration Gala Night | Create VIP guest list and seating plan | In Progress | Chris Brown | 2024-04-14 | 70%
2024-04-09 | Sustainability Summit 2024 | Finalize speaker bios and headshots | In Progress | Jessica Taylor | 2024-04-13 | 55%
2024-04-09 | Sustainability Summit 2024 | Confirm registration platform setup | Pending | Taylor King | 2024-04-15 | 20%
Daily Summary - Total Tasks: 11 ¦ In Progress: 5 ¦ Pending: 6 ¦ Completed: 0