## Worksheet
Event Planning Project Tracker
Dashboard View - Monitor all key milestones, tasks, and deadlines
Event Name | Task/Phase | Owner | Due Date | Status | Progress
Event: Annual Conference 2024
Annual Conference 2024 | Initial Planning & Budgeting | Sarah Johnson | 2024-01-15 | In Progress
Annual Conference 2024 | Speaker Selection & Confirmations | Michael Chen | 2024-01-30 | In Progress
Annual Conference 2024 | Venue Booking & Contract Finalization | Lisa Park | 2024-01-18 | Pending
Event: Wedding Ceremony
Wedding Ceremony | Vendor Contracts Finalization | Amy Rodriguez | 2024-03-10 | Completed
Wedding Ceremony | Guest List & Invitations | Amy Rodriguez | 2024-02-15 | In Progress
Event: Corporate Gala
Corporate Gala | Marketing & Promotion Campaign | Daniel Thompson | 2024-05-15 | Delayed
Corporate Gala | Final Venue Inspection & Setup | Daniel Thompson | 2024-05-10 | Pending
Project Tracker Dashboard ¦ Last updated: April 5, 2024 ¦ Total Events: 3 ¦ Active Tasks: 6