## Worksheet
Event Planning - Project Tracker (Data Version)
Track milestones, responsibilities, and timelines for successful event execution.
Task ID | Task Name | Description | Responsible Team Member | Start Date | Due Date | Status | Priority Level
EVT-001 | Finalize Event Concept & Theme | Define core theme, branding, and target audience. | Jane Smith | 2024-11-05 | 2024-11-15 | In Progress | High
EVT-002 | Secure Venue & Permits | Negotiate contract and obtain necessary permits. | Mike Johnson | 2024-11-16 | 2024-12-05 | Pending | High
EVT-003 | Develop Guest List & Invitations | Create digital and printed invites with RSVP tracking. | Sarah Lee | 2024-11-25 | 2024-12-15 | Pending | Medium
EVT-004 | Arrange Catering & Food Services | Select vendors and finalize menu options. | Tom Brown | 2024-12-16 | 2025-01-05 | Pending | High
EVT-005 | Coordinate Entertainment & Speakers | Book performers and confirm speaker availability. | Alice Williams | 2024-12-18 | 2025-01-10 | Pending | Medium
EVT-006 | Finalize Event Schedule & Logistics | Compile timeline, map out staffing, and set up tech setup. | Daniel Kim | 2025-01-11 | 2025-01-30 | Pending | High
EVT-007 | Conduct Final Event Walkthrough | Review all elements with team and stakeholders. | Jane Smith | 2025-01-31 | 2025-02-03 | Pending | High
Total Tasks:7 ¦Completed:0 ¦In Progress:1 ¦Pending:6