## Worksheet
Event Planning - Project Tracker (Extended)
Task ID | Task Name | Description | Assigned To | Start Date | Due Date | Status | Budget (USD) | Progress (%) | Dependencies | Milestones Reached
T001 | Finalize Event Concept & Theme | Define the core theme, purpose, and key elements of the event. | Jane Doe | 2025-04-15 | 2025-04-30 | In Progress | $1,500.00 |  | None | Theme Approval Received
T002 | Select & Book Venue | Research, visit, and contract with a suitable venue. | Mike Johnson | 2025-04-18 | 2025-05-10 | Pending | $15,000.00 |  | T001 | N/A
T003 | Develop Marketing & Promotion Plan | Create content calendar, social media strategy, and outreach. | Sarah Lee | 2025-04-16 | 2025-06-30 | In Progress | $8,750.00 |  | T001 | Initial Campaign Draft Submitted
T004 | Secure Keynote Speaker | Contact, negotiate, and confirm the main speaker. | Chris Brown | 2025-04-25 | 2025-05-15 | Delayed | $7,800.00 |  | T002 | N/A
T005 | Plan Event Schedule & Logistics | Map out timeline, sessions, speaker order, and flow. | Lisa Wang | 2025-04-19 | 2025-05-31 | In Progress | $6,300.00 |  | T001, T002 | Schedule Draft Approved
T006 | Manage Vendor Contracts & Deliverables | Negotiate with caterers, AV, décor, and security. | David Park | 2025-04-28 | 2025-06-15 | Pending | $34,980.00 |  | T002, T005 | N/A
T007 | Finalize Guest List & RSVP Management | Compile invitees, send invitations, track confirmations. | Amy Roberts | 2025-05-12 | 2025-07-14 | Pending | $3,460.00 |  | T005 | N/A
T008 | Conduct Event Run-Through & Rehearsal | Full dress rehearsal with speakers, staff, and tech. | 2025-07-19 | 2025-08-31 | Completed | $4,150.00 |  | T005, T006 | Rehearsal Completed Successfully
© 2025 Event Planning Project Tracker ¦ Last Updated: April 3, 2025