## Worksheet
Task ID | Task Description | Assigned To | Status | Budget (USD) | Actual Cost (USD) | Remaining Budget (USD)
T001 | Event Venue Booking | Jane Smith | In Progress | 5,000.00 | 4,250.75 | 749.25
T002 | Marketing & Promotions | Mark Johnson | Completed | 3,500.00 | 3,412.50 | 87.5
T003 | Catering Services | Lisa Chen | On Hold | 6,800.00 | 1,250.35 | 5,549.65
T004 | Audio/Visual Equipment Rental | Daniel Brooks | In Progress | 2,750.00 | 1,986.42 | 763.58
T005 | Speaker Fees & Travel Arrangements | Sarah Wilson | Pending Approval | 4,200.00 | 1,839.67 | 2,360.33
T006 | Event Staffing & Volunteer Management | Chris Taylor | In Progress | 2,950.00 | 1,782.44 | 1,167.56
T007 | Decoration & Branding Materials | Amanda Green | Completed | 1,800.00 | 1,543.28 | 256.72
Total Budgeted Cost: |  |  |  | $27,000.00 | $16,455.41 | $10,544.59