## Event Planning Project Tracker
Event Planning Project Tracker - Home Use
Task ID | Task Description | Responsible Person | Due Date | Status | Progress (%)
T001 | Define Event Theme & Objective | Jane Doe | 2024-04-15 | Pending | 10%
T002 | Select Venue & Confirm Booking | John Smith | 2024-04-18 | Pending | 5%
T003 | Create Guest List & Send Invitations | Jane Doe | 2024-04-25 | Pending | 15%
T004 | Arrange Catering & Menu Approval | Mike Johnson | 2024-04-20 | Pending | 8%
T005 | Hire Entertainment (Band/DJ) | Sarah Williams | 2024-04-16 | Pending | 7%
T006 | Design & Print Invitations | Lisa Brown | 2024-04-28 | Pending | 12%
T007 | Coordinate Decorations & Setup Plan | Jane Doe | 2024-04-30 | Pending | 5%
T008 | Confirm Transportation for Guests | John Smith | 2024-05-15 | Pending
T009 | Create Event Schedule & Timeline | Sarah Williams | 2024-04-17 | Pending | 6%
T010 | Finalize Budget & Expense Tracking | Lisa Brown | 2024-04-23
Note:This is a home use project tracker for event planning purposes.