## Event Planning Project Tracker
Event Planning Project Tracker
Task ID | Task Description | Assigned To | Start Date | Due Date | Status
#ET-001 | Define event theme and objectives | Sarah Johnson | 2024-03-15 | 2024-03-18 | In Progress
#ET-002 | Secure event venue and confirm contract | Michael Chen | 2024-03-16 | 2024-03-19 | Pending
#ET-003 | Develop event budget and cost projections | Emily Rodriguez | 2024-03-15 | 2024-03-17 | Completed
#ET-004 | Design and send invitations (digital & print) | Lisa Thompson | 2024-03-17 | 2024-03-21 | In Progress
#ET-005 | Coordinate with vendors (catering, AV, decor) | David Kim | 2024-03-16 | 2024-03-19 | Pending
#ET-006 | Finalize event program and speaker list | Sarah Johnson | 2024-03-18 | 2024-03-21 | In Progress
#ET-007 | Conduct final walkthrough at venue | Michael Chen | 2024-03-25 | 2024-03-26 | Pending
#ET-008 | Prepare on-site event materials and signage | Lisa Thompson | 2024-03-24 | 2024-03-25 | Pending
Project Overview
Total Tasks:8 ¦Completed:1 ¦In Progress:3 ¦Pending:4
Total Budget: $25,000 ¦ Current Spend: $7,850 (31.4%)
Event Planning Project Tracker - © 2024 ¦ Large Business Template