## Event Planning Project Tracker
Event Planning Project Tracker
Office Use ¦ Version: 1.0 ¦ Created for Efficient Event Management
Task ID | Task Description | Assigned To | Start Date | End Date | Status | % Complete
T001 | Finalize Event Concept & Theme | Jane Smith | 2024-05-15 | 2024-05-18 | In Progress | 75%
T002 | Select Venue & Confirm Booking | Mark Lee | 2024-05-16 | 2024-05-23 | Pending Approval | 30%
T003 | Catering Menu Finalization | Lisa Wong | 2024-05-17 | 2024-05-19 | Completed | 100%
T004 | Invitation Design & Distribution Plan | Daniel Reed | 2024-05-18 | 2024-05-31 | In Progress | 60%
T005 | Schedule Speakers & Presenters | Sarah Kim | 2024-05-19 | 2024-05-27Pending Confirmation | 45%
T006 | Create Event Schedule & Agenda | James Brown | 2024-05-21 | 2024-05-31 | In Progress | 70%
T007 | Marketing & Social Media Campaign Launch | Amanda Perez | 2024-05-222024-06-15Pending Start | 0%
T008 | Onsite Logistics & Staffing Plan | Tom Harris | 2024-05-23 | 2024-06-10 | In Progress | 55%
T009 | Event Registration Portal Setup | Fiona Clarke | 2024-05-242024-06-14Pending Start | 5%
T010 | Dress Rehearsal & Final Run-through | All Team Members | 2024-06-13 | 2024-06-14 | To Do | 0%
Last Updated: May 20, 2024 ¦ Prepared by: Project Management Office
For internal use only – Do not distribute without authorization.