## Worksheet
Event Planning - Project Tracker (Planning View)
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | % Complete
T001 | Define Event Goals & Objectives | Project Manager | 2024-03-05 | 2024-03-15 | Pending | 15%
T002 | Select Event Date & Venue | Logistics Coordinator | 2024-03-16 | 2024-03-31 | In Progress | 65%
T003 | Develop Marketing Strategy | Marketing Lead | 2024-03-18 | 2024-04-15 | In Progress | 75%
T004 | Send Invitations & RSVPs | Event Coordinator | 2024-03-31 | 2024-05-15 | Pending | 8%
T005 | Finalize Catering & Menu Options | Catering Manager | 2024-04-10 | 2024-05-15 | In Progress | 68%
T006 | Coordinate Audio/Visual Setup | Technical Lead | 2024-05-15 | 2024-06-15 | Pending | 3%
T007 | Finalize Event Schedule & Agenda | Project Manager | 2024-05-25 | 2024-06-15 | Pending | 1%
T008 | Conduct Final Event Walkthrough | Event Coordinator | 2024-06-15 | 2024-06-15 | Overdue | 95%