## Worksheet
Event Planning - Project Tracker Report
Project:Annual Company Conference 2024
Date Range:January 15, 2024 – June 30, 2024
Status as of:May 18, 2024
Task ID | Task Description | Responsible Team | Start Date | Due Date | Status | % Complete
EVT-001 | Finalize event concept and theme | Marketing & Planning Team | Jan 15, 2024 | Jan 31, 2024 | Completed | 100%
EVT-002 | Secure venue and confirm capacity | Logistics Team | Feb 1, 2024 | Feb 15, 2024 | Completed | 100%
EVT-003 | Develop event agenda and speaker lineup | Program Committee | Feb 16, 2024 | Mar 5, 2024 | Completed | 100%
EVT-004 | Publish event registration and ticketing portal | IT & Marketing Team | Mar 6, 2024 | Mar 15, 2024 | Completed | 100%
EVT-005 | Begin attendee outreach and marketing campaign | Marketing Team | Mar 16, 2024 | Apr 30, 2024 | In Progress | 85%
EVT-006 | Finalize sponsor packages and secure partners | Sponsorship Team | Mar 16, 2024 | May 15, 2024 | In Progress | 78%
EVT-007 | Coordinate on-site logistics and vendor contracts | Logistics Team | Apr 1, 2024 | May 31, 2024 | In Progress | 65%
EVT-008 | Conduct final rehearsals and tech checks | Production Team | Jun 20, 2024 | Jun 25, 2024 | Delayed | 30%
EVT-009 | Finalize event evaluation and feedback system | Planning Team | Jun 15, 2024 | Jun 30, 2024 | Delayed | 15%