## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Status
EVT-001 | Finalize Event Concept and Theme | Jane Smith | 2023-10-01 | 2023-10-05 | To Do
EVT-002 | Secure Venue and Confirm Booking | Mike Johnson | 2023-10-03 | 2023-10-15 | In Progress
EVT-003 | Develop Guest List and Send Invitations | Sarah Lee | 2023-10-10 | 2023-10-25 | In Progress
EVT-004 | Coordinate Catering and Menu Approval | David Brown | 2023-10-12 | 2023-10-28 | In Progress
EVT-005 | Arrange Audio/Visual Equipment and Setup | Lisa White | 2023-10-15 | 2023-11-01 | To Do
EVT-006 | Confirm Speaker and Schedule Presentation | James Wilson | 2023-10-18 | 2023-11-05 | To Do
EVT-007 | Finalize Event Schedule and Timeline | Jane Smith | 2023-11-01 | 2023-11-05 | To Do
EVT-008 | Conduct Event Dry Run and Review Feedback | All Team Members | 2023-11-06 | 2023-11-07 | To Do
EVT-009 | Execute Event and Manage On-site Operations | All Team Members | 2023-11-08 | 2023-11-08 | To Do
EVT-010 | Post-event Follow-up and Thank You Communications | Sarah Lee | 2023-11-09 | 2023-11-15 | To Do