## Worksheet
Event Planning Project Tracker
Startup Style Template • Purpose: Event Planning • Project Status Overview
Task ID | Task Description | Assigned To | Due Date | Status | Priority
#EV001 | Finalize event venue booking and contract signing | Jane Smith | 2023-10-15 | Pending | High
#EV002 | Confirm guest list and send invitations | Mark Johnson | 2023-10-18 | In Progress | High
#EV003 | Develop event marketing campaign and social media strategy | Sarah Lee | 2023-10-22 | In Progress | Medium
#EV004 | Coordinate catering and meal plan approval | Carlos Mendez | 2023-10-16 | In Progress | High
#EV005 | Arrange audiovisual and stage setup for presentations | Alice Brown | 2023-10-17 | Pending | Medium
#EV006 | Prepare event agenda and speaker schedule | James Wilson | 2023-10-19 | Completed | Medium
#EV007 | Organize team onboarding and briefing session | Emma Davis | 2023-10-14 | Completed | Low
#EV008 | Review and finalize event budget report | Liam Chen | 2023-10-13 | Completed | High
#EV009 | Confirm transportation and shuttle services for attendees | Natalie Kim | 2023-10-20 | Pending | High
#EV010 | Set up event registration and ticketing system | Oliver Taylor | 2023-10-12 | Completed | Medium
Project Overview:Total tasks:10¦ In Progress:3¦ Pending:3¦ Completed:4
Next Milestone:Finalize event logistics by October 25, 2023