## Worksheet
Event Planning - Project Tracker (Summary View)
Task ID | Task Name | Category | Assigned To | Start Date | Due Date | Status | Budget (USD)
T001 | Define Event Scope & Objectives | Planning | Jane Smith | 2024-05-15 | 2024-05-18 | Completed | $0.00
T002 | Book Venue & Confirm Availability | Logistics | Mike Johnson | 2024-05-16 | 2024-05-23 | Upcoming | $8,500.00
T003 | Secure Catering Provider | Logistics | Sarah Lee | 2024-05-17 | 2024-05-25 | Upcoming | $3,750.00
T004 | Design Event Invitations & Promotions | Marketing | David Brown | 2024-05-18 | 2024-05-30 | Completed | $1,250.00
T005 | Send Out Invitations (Email & Print) | Marketing | Sarah Lee | 2024-05-26 | 2024-06-15 | Upcoming | $975.00
T006 | Coordinate Audio/Visual Setup & Tech Team | Logistics | Tom Wilson | 2024-05-31 | 2024-06-10 | Upcoming | $4,350.00
T007 | Finalize Speaker Confirmations & Agendas | Planning | Jane Smith | 2024-06-01 | 2024-06-18 | Upcoming | $750.00
T008 | Onsite Event Coordination & Staff Briefing | Execution | Mike Johnson | 2024-06-23 | 2024-06-30 | Delayed | $5,850.00
Project Summary
Total Tasks: | 8
Completed: | 2
Upcoming: | 5
Delayed: | 1
Total Budget Spent: | $25,475.00