## Worksheet
Event Planning Project Tracker - Team Use
Task ID | Task Description | Assigned To | Due Date | Status | Priority | Budget Allocated ($)(Total: $10,000)
#ET-24-01 | Finalize Event Concept & Theme | Sarah Johnson | 2024-05-15 | Pending | High | $1,200(12%)
#ET-24-02 | Book Venue & Confirm Capacity | Michael Chen | 2024-05-18 | In Progress | High | $3,500(35%)
#ET-24-03 | Secure Catering Provider | Lisa Rodriguez | 2024-05-20 | In Progress | Medium | $1,800(18%)
#ET-24-04 | Design Invitations & Digital Assets | James Wilson | 2024-05-25 | Pending | Medium | $600(6%)
#ET-24-05 | Coordinate Speaker & Guest Appearances | Amanda Taylor | 2024-05-30 | Pending | High | $850(8.5%)
#ET-24-06 | Develop Event Schedule & Timelines | Daniel Kim | 2024-05-17 | In Progress | High | $350(3.5%)
#ET-24-07 | Arrange Audiovisual & Technical Setup | Nina Patel | 2024-06-01 | Pending | Medium | $750(7.5%)
#ET-24-08 | Send Out Invitations & Track RSVPs | Emily Davis | 2024-06-10 | Pending | Low | $250(2.5%)
Total Budget Spent: | [5 empty] | $9,300(93%)
Notes:This tracker is updated weekly. Team members are expected to report progress every Friday by 5 PM.
Last Updated:April 5, 2024 ¦Status Legend:Pending (yellow), In Progress (light blue), Completed (light green)