## Worksheet
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | % Complete
EVT-001 | Finalize venue booking | Sarah Johnson | 2023-10-15 | 2023-10-25 | Pending Review | 45%
EVT-002 | Confirm catering menu | James Lee | 2023-10-18 | 2023-11-05 | In Progress | 65%
EVT-003 | Send invitations to guests | Linda Chen | 2023-10-20 | 2023-11-15 | Not Started | 5%
EVT-004 | Arrange transportation for VIPs | Mike Rodriguez | 2023-10-25 | 2023-11-18 | Pending Review | 70%
EVT-005 | Finalize event program schedule | Alice Thompson | 2023-11-01 | 2023-11-25 | In Progress | 85%
EVT-006 | Arrange on-site registration desk | Daniel Kim | 2023-11-10 | 2023-11-30 | Not Started | 0%
EVT-007 | Hire and brief event staff | Sophia Patel | 2023-11-15 | 2023-12-05 | In Progress | 30%
EVT-008 | Finalize post-event feedback form | Robert Brown | 2023-11-28 | 2023-12-15 | Not Started | 0%
Project Overview
Total Tasks:8 ¦In Progress:3 ¦Pending Review:2 ¦Not Started:3
Average Completion Rate:45%