## Worksheet
Week of | Task Name | Owner | Status | Due Date | Progress (%)
2023-10-02 | Vendor Contracts Finalized | Jane Doe | In Progress | 2023-10-15 | 65%
2023-10-02 | Schedule Venue Visit | John Smith | To Do | 2023-10-10 | 0%
2023-10-02 | Catering Menu Approval | Sarah Lee | Completed | 2023-10-08 | 100%
2023-10-09 | Promotional Materials Design | Alex Johnson | In Progress | 2023-10-18 | 45%
2023-10-09 | Dress Rehearsal Setup | Maria Garcia | To Do | 2023-10-17 | 0%