## Worksheet
Event Planning Savings TrackerGenerated on:
Page 1 - Overview Summary
Category | Budgeted Amount ($) | Actual Spent ($) | Remaining ($) | Status
Venue Rental | 3,500.00 | 3,250.00 | 250 | In Budget
Catering & Food | 4,800.00 | 4,675.33 | 124.67 | In Budget
Decorations & Styling | 2,200.00 | 1,985.40 | 214.6 | In Budget
DJ / Entertainment | 1,500.00 | 1,357.89 | <142.11 | In Budget
Photography & Video | 2,800.00 | 2,673.55 | 126.45 | In Budget
Total Budgeted | $14,800.00 | $13,942.17 | $857.83
Page 2 - Detailed Expense Tracker
Date | Description | Category | Amount ($) | Status (Paid/Outstanding)
2024-01-05 | Booking deposit - Grand Ballroom | Venue Rental | 750 | Paid
2024-01-18 | Catering quote approval (35 guests) | Catering & Food | 899.75 | Paid
2024-01-25 | Floral arrangements - centerpieces & arches | Decorations & Styling | 638.45 | Paid
2024-02-01 | DJ booking confirmation (3 hours) | DJ / Entertainment | 750 | Paid
2024-02-15 | Photographer contract signed - full day coverage | Photography & Video | 1,389.50 | Paid
Additional expenses to track:
2024-03-10 | Balloons & lighting rental (extra) | Decorations & Styling | 189.25 | Paid
2024-03-20 | Rental of event chairs & tables (additional 30) | Venue Rental | 315.75 | Paid
Total Spent to Date: |  |  |  | $13,942.17
Page 3 - Savings Goals & Progress
Savings Goal | Target Amount ($) | Current Saved ($) | Progress (%)
Budget Cushion (10%) | 1,480.00 | 1,385.27 | 93.6%
Unexpected Costs Reserve | 500 | 472.83 | 94.6%
Total Savings Goal: | $1,980.00 | $1,858.10 | 93.8%
Page 4 - Event Planning Timeline & Milestones
Date | Milestone | Status (Completed / Pending) | Notes
2023-11-01 | Event theme & concept finalized | Pending | Theme: Tropical Luau
2024-01-15 | Venue booked & deposit paid | Completed | Awaiting contract signature.
2024-01-31 | Catering vendor confirmed & menu finalized | Completed | Dietary options included.
2024-02-15 | DJ and photographer hired & contract signed | Completed | All services in place.
Upcoming Milestones:
2024-03-10 | Send invitations (digital & print) | Pending | Design approved.
2024-03-25 | Dress rehearsal & setup walkthrough | Pending | Tent setup inspection needed.