## Event Planning Schedule Planner
Event Planning Schedule Planner
Event Name | Date | Time Slot | Location | Team Responsible | Status | Prioritization Level
Planning & Preparation Phase
Initial Planning Meeting | 2023-10-05 | 14:00 - 16:00 | Conference Room A | Project Lead, Logistics Team | In Progress | Medium
Vendor Selection & Contracts | 2023-10-10 | 10:00 - 12:30 | Remote / Office | Venue Coordinator, Finance Team | Pending | High
Execution Phase
Decoration Setup | 2023-11-15 | 08:00 - 14:00 | Main Hall, Event Center | Decor Team, Volunteers | Completed | Low
Audio-Visual Installation | 2023-11-15 | 09:00 - 15:00 | Main Hall, Event Center | AV Team, IT Support | In Progress | Medium
Finalization & Day-of Execution
Final Walkthrough & Rehearsal | 2023-11-16 | 10:00 - 13:00 | Main Hall, Event Center | All Teams, Event Manager | Pending | High
Day-of Event Coordination | 2023-11-17 | 07:00 - 22:00 | Main Hall, Event Center | Event Manager, Support Staff | Pending | High
Post-Event Activities
Debrief Meeting & Documentation | 2023-11-20 | 14:00 - 16:30 | Conference Room B | All Leads, Project Manager | Not Started | Low
Vendor Payment Processing | 2023-11-25 | Flexible (Remote) | Finance Department | Finance Team, Accountant | Not Started | Medium