## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Status | Budget Allocated ($) | Prioritization Level
TP-001 | Finalize Event Concept & Theme | Jane Doe | 2024-04-05 | 2024-04-15 | Completed | 8,500 | High
TP-002 | Schedule Venue Booking & Site Visit | Mike Chen | 2024-04-16 | 2024-05-15 | In Progress | 12,300 | High
TP-003 | Develop Marketing & Promotion Plan | Sarah Kim | 2024-04-18 | 2024-05-31 | In Progress | 6,750 | Medium
TP-004 | Craft Guest List & Send Invitations | Liam Patel | 2024-05-15 | 2024-06-30 | Pending | 3,250 | Medium
TP-005 | Coordinate Catering & Dietary Requirements | Aisha Johnson | 2024-06-15 | 2024-07-15 | Pending | 9,875 | High
TP-006 | Arrange Entertainment & Performers | Tom Reynolds | 2024-06-15 | 2024-07-31 | Pending | 7,450 | Medium
TP-007 | Crew & Volunteer Coordination | Elena Rodriguez | 2024-06-25 | 2024-08-15 | Pending | 4,300 | Medium
TP-008 | Finalize Event Run Sheet & Timeline | Jane Doe | 2024-07-31 | 2024-08-15 | In Progress | 2,850 | High
TP-009 | Post-Event Survey & Feedback Collection | Sarah Kim | 2024-08-16 | 2024-08-31 | Pending | 1,250 | Low
Total Budget Allocated:$67,425
Tasks Completed:1 / 9 (11.1%)
Tasks In Progress:2 / 9 (22.2%)
Tasks Pending:6 / 9 (66.7%)