## Worksheet
Event Planning Schedule Planner - Data Version
Date | Task/Activity | Assignee | Status | Notes/Details
2023-10-05 | Finalize Event Concept and Theme | Jane Doe | Completed | Theme selected: "Galaxy Night"
2023-10-10 | Secure Venue Booking | John Smith | In Progress | Pending confirmation from venue manager
2023-10-15 | Create Guest List & Send Invitations | Sarah Johnson | Not Started | Email template drafted, awaiting approval
2023-10-20 | Coordinate Catering Services | Mike Brown | Not Started | Caterer shortlisted; need to schedule tasting
2023-10-25 | Design and Print Invitations | Lisa White | Not Started | Artwork in progress, deadline: 10/18
2023-11-01 | Confirm Audio/Visual Setup | David Lee | Not Started | Vendor quote pending
2023-11-05 | Conduct Final Event Walkthrough | Jane Doe | Not Started | Schedule with venue manager to be confirmed
Status Legend:
Completed– Task finished and verified
In Progress– Task is currently being worked on
Not Started– Task has not yet begun