## Worksheet
Event Planning Schedule Planner - Detailed
Time Slot | Date | Pre-Event Phase |  |  | Event Execution |  |  |  | Post-Event Phase
|  | Planning & Research | Vendor Coordination | Logistics Setup | Schedule & Timeline Maintenance | On-Site Management (Staff/Setup) | Celebration/Activity Execution | Fallback & Issue Resolution | Debriefing & Reporting | Budget Reconciliation | Celebration Follow-up
08:00 - 09:30 | 2024-11-25 | ✓ Strategy Meeting [Team] | ✓ Confirm Catering [Vendor] | ✓ Verify Equipment Arrival [Logistics] | ✓ Finalize Timeline & Assign Roles | ✓ Setup Stage & Audio | - | - | ✗ Not Applicable | - | Pre-Event Prep Complete ✅ 100%
09:30 - 11:00 | 2024-11-25 | ✓ Define Theme & Guest List [Lead Planner] | ✓ Confirm Decor Vendor [Contract Signed] | ✓ Deliver Chairs & Tables | ✓ Finalize Staff Rotas | ✓ Check Lighting & Sound Tests | - | - | Post-Event Summary Ready ✅ 100%
11:00 - 12:30 | 2024-11-25 | ✓ Finalize Invitations [Send Draft] | ✓ Confirm Music & DJ [Soundcheck Scheduled] | ✓ Verify Permit & Safety Checks | - | ✓ Rehearsal Run-through | -
Event Day: 2024-11-26 (Monday) |  | ✅ All Pre-Event Tasks Complete |  |  | ✓ Final Countdown [0 Hrs] | ✓ Welcome Guests & Registration | ⚠️ Monitor Flow [10:45 AM] | ✅ All Post-Event Tasks Initiated
12:30 - 14:00 | 2024-11-26 | - | - | - | 🎉 Main Event Session [Keynote, Networking, Awards]
14:00 - 15:30 | 2024-11-26 | - | - | 🎉 Workshop Sessions [Parallel Tracks]
15:30 - 17:00 | 2024-11-26 | 🎉 Closing Ceremony [Thank You, Feedback Collection] |  |  |  | 📋 Debriefing Begins [Team Meeting]
17:00 - 18:30 | 2024-11-26 | 🗜️ Breakdown & Cleanup [Staff Coordinated] |  |  |  |  | 🔄 Budget Reconciliation Phase [Receipts Verified]
18:30 - 20:00 | 2024-11-26 | 📦 Equipment Return & Storage [All Items Logged] |  |  |  |  | ✉️ Post-Event Survey Sent [To Guests]
Note:This template supports detailed tracking across all phases of event planning with color-coded progress indicators and role-based responsibilities.