## Event Planning Schedule Planner
Event Planning Schedule Planner
Time Slot | Date | Event Activity | Location | Responsible Person(s) | Status | Notes/Requirements
Day 1: Setup & Preparation (June 5, 2024)
08:00 - 10:00 | Jun 5, 2024 | Arrival & Site Inspection | Main Conference Hall | Jane Smith (Coordinator) | Pending | Check power outlets, AV setup, signage placement.
10:30 - 12:00 | Jun 5, 2024 | Stage & Equipment Setup | Main Conference Hall | Technical Team (Mike & Lisa) | In Progress | Assemble stage, install sound system.
Day 2: Final Preparations (June 6, 2024)
09:00 - 11:30 | Jun 6, 2024 | Decor & Branding Installation | Main Hall, Registration Area | Design Team (Sarah & Tom) | Pending | Hang banners, set up welcome table.Confirm brand colors and fonts.
Day 3: Event Execution (June 7, 2024)
08:00 - 10:30 | Jun 7, 2024 | Registration & Guest Check-In | Entrance Lobby | Diana (Front Desk), Volunteers (5) | Pending | Print name badges, distribute event kits.Verify attendee list.Rush setup if needed.
Day 4: Wrap-Up & Cleanup (June 8, 2024)
16:00 - 18:30 | Jun 8, 2024 | Cleanup & Equipment Return | All Areas | Janitorial Staff (4), Logistics Team (Mark) | Not Started | Restore venue to original condition.Return borrowed items.Tally inventory list.
Note:This schedule is subject to change. Please update status regularly and notify the team of any delays or issues.
Last Updated: May 30, 2024