## Worksheet
Event | Date & Time | Location | Budget (USD) | Actual Spend (USD) | Status | Notes
Venue Booking | 2024-03-15, 10:00 AM | Grand Ballroom, Downtown Hotel | $5,000.00 | $4,950.75 | Completed | Invoices received and verified.
Catering | 2024-03-15, 12:30 PM | On-site Kitchen | $7,500.00 | $7,425.30 | Completed | Menu finalized and approved.
Audio/Visual Setup | 2024-03-15, 11:00 AM | Main Stage Area | $3,200.00 | $3,150.25 | Completed | Equipment delivered on time.
Decor & Lighting | 2024-03-15, 08:30 AM | Event Hall Interior | $4,800.00 | $4,725.10 | In Progress | Delivery delayed by one day.
Guest Registration | 2024-03-15, 09:00 AM | Entrance Lobby | $1,200.00 | $1,205.45 | In Progress | Online system still being tested.
Speaker Coordination | 2024-03-15, 10:30 AM | Main Stage | $2,500.00 | $2,495.60 | Completed | All speakers confirmed and briefed.
Total Budget |  |  | $24,200.00 | $23,952.45